## Issues
Area | Issue | Outcome | Owner
General Flow | Check general flow - OK?
General Flow | Is the flow of Lock, Schedule, Complete OK?
General Flow | At what point are amendments prevented - Locking?
Emails | What (if any) actions require an email notification?
Amendments | At what stages do Amendments need 'approving'?
Validation | Validate selected action according to current status
Validation | Don't allow update to status if amendments pending (see above)
Workflow | Review +n days
Validation | Validate expected input vs actual bill of materials?
Validation | Required Date before submit request
Initial Request | Fields - optional and mandatory?
Complete request | Fields - optional and mandatory?
Bill Of Materials | Start with x rows
Amendments | Include User & Current Status?
Amendments | Send email? Trigger task to accept?
Tasks | Include In Calendar?
Access Control | Tighten up acces control
Flow | Implement chnages to flow as discussed 15/6/2010 - i.e. Once scheduled the flow is complete. Lock 24h before expected process date.
EMails | Only on complete request & amendments after scheduling
API Class | Check how shoudl work when part of package.

## TO DO
Task | Owner | Due | Completed
Provide Consolidated Request Sheet | Martyn
Additonal Fields for Order Book | Martyn
Provide examples of required Reports | Martyn
Install in Martyn's env | Lee | 2010-06-17
Implement consolidated request sheet fields | Lee
Implement order book fields | Lee
Implement sample reports (3?) | Lee
Implement exports to XL ( if required) | Lee